## Steps
Todo App: Software Engineering Learning Tracker
Legend: change only the yellow Status cells (dropdown: Not started / In progress / Done). Everything else updates automatically.
# | Step | What you do | Session | Status
1 | Requirements | Write 3 user stories and a "not doing" line in README.md | Session 1 | Done
2 | Environment | Install Python and Git, create and activate .venv | Session 1 | Done
3 | Version control | git init, .gitignore, first commits | Session 1 | Done
4 | Code with TDD | Write a failing test, write the smallest code to pass, refactor. Repeat for add, list, done | Session 1 | In progress
5 | Testing | Run python -m pytest, add edge cases (empty list, bad number), save packages in requirements.txt | Session 1 | Not started
6 | Linting and formatting | Install ruff, run ruff check and ruff format, fix what it flags | Session 1 | Not started
7 | Branches and pull requests | Create a GitHub repo, git remote add origin, push, make a feature branch, open a PR, review it yourself, merge | Session 2 | Not started
8 | CI | Add a GitHub Actions file that runs pytest and ruff on every push and PR | Session 2 | Not started
9 | Packaging and release | Add pyproject.toml so it installs as a todo command, finish the README, tag v0.1.0 | Session 2 | Not started
10 | Maintenance | Introduce a bug, file an issue, write a failing test, fix it, close the issue | Session 2 | Not started
| Steps done | 3
| Total steps | 10
| Progress | 30%